Test Plan Document

SmartCart E-Commerce Platform — Phase 02

| Project | SmartCart QA Ecosystem |
| --- | --- |
| Phase | 02 — Test Planning |
| Prepared By | Adit Gupta — QA Lead |
| Version | 1.0 |
| Date | March 2025 |
| Status | Approved |

# 1. Introduction

## 1.1  Purpose

This Test Plan defines the overall QA strategy for SmartCart, covering all testing activities from unit-level validation through performance and security testing. It establishes scope, approach, tools, timelines, and risk mitigations.

## 1.2  References

- SmartCart Business Requirement Document v1.0

- OpenAPI 3.0 Specification — SmartCart Backend

- SmartCart Architecture Diagram (Phase 04)

# 2. Test Objectives

| # | Objective |
| --- | --- |
| 1 | Verify all functional requirements defined in the BRD |
| 2 | Validate API contracts against the OpenAPI 3.0 specification |
| 3 | Ensure UI consistency across Chrome, Firefox, Safari, and Edge |
| 4 | Validate system performance under 100 and 500 concurrent users |
| 5 | Identify and report all defects with Severity >= Medium before release |
| 6 | Achieve >= 95% automation coverage across API and UI layers |

# 3. Test Scope

## 3.1  In-Scope

| Module | Test Types Applicable |
| --- | --- |
| User Authentication | Functional, Security (OWASP), API, Regression |
| Product Catalog | Functional, UI (cross-browser), API, Performance |
| Cart Management | Functional, API, Concurrency, Regression |
| Checkout | Functional, End-to-End, Regression |
| Payment Gateway | Functional, Integration (sandbox), Negative, Regression |
| Admin Dashboard | Functional, Authorization, API, Regression |
| REST API Layer | Contract, Schema, Status Codes, Performance |

## 3.2  Out-of-Scope

- Mobile native application testing (iOS / Android)

- Third-party payment gateway internal system testing

- Infrastructure penetration / network-level security testing

# 4. Test Strategy

## 4.1  Test Levels

| Level | Owner | Approach / Tools |
| --- | --- | --- |
| Unit Testing | Developers | JUnit 5 / Jest — executed by dev team pre-handoff |
| Integration Testing | SDET | API contract validation via Rest Assured / Karate |
| System Testing | SDET | End-to-end scenario coverage against QA environment |
| Regression Testing | SDET (Auto) | Automated suite triggered on every PR merge via GitHub Actions |
| Performance Testing | SDET | JMeter 5.6 + k6 — load, stress, and spike scenarios |
| Security Testing | SDET | OWASP Top 10 checks embedded in API test suite |

## 4.2  Test Types

| Test Type | Description | Trigger |
| --- | --- | --- |
| Functional | Verify each feature against acceptance criteria | Every sprint |
| API | REST endpoint validation — status codes, schema, auth | Every PR |
| UI / E2E | Selenium WebDriver + Playwright cross-browser flows | Every sprint |
| Performance | Load (100 VUs), Stress (500 VUs), Spike | Pre-release |
| Security | OWASP Top 10 — SQLi, XSS, Auth bypass | Every sprint |
| Regression | Full automated suite re-run to catch regressions | Every merge |

# 5. Tools & Technology Stack

| Category | Tool | Version |
| --- | --- | --- |
| API Automation | Rest Assured | 5.3.2 |
| API Automation | Karate Framework | 1.4.1 |
| UI Automation | Selenium WebDriver | 4.16.1 |
| UI Automation | Playwright | 1.40+ |
| Performance | Apache JMeter | 5.6.2 |
| Performance | k6 | 0.48+ |
| Reporting | Allure Reports | 2.24.0 |
| CI/CD | GitHub Actions | Latest |
| Monitoring | Prometheus | Latest |
| Monitoring | Grafana | Latest |
| Test Management | JIRA + Xray | Cloud |
| AI Augmentation | Claude API | Anthropic |

# 6. Test Environments

| Environment | Purpose | Base URL | Data |
| --- | --- | --- | --- |
| Dev | Developer smoke tests | http://dev.smartcart.local | Dev seed |
| QA | Primary test execution | http://qa.smartcart.local | Full seed set |
| Staging | Pre-release validation | http://staging.smartcart.local | Prod-like data |
| Production | Post-deploy smoke tests only | https://smartcart.com | Live data (read-only) |

# 7. Entry & Exit Criteria

## 7.1  Entry Criteria (Start Testing)

| Criterion | Verification Method |
| --- | --- |
| All user stories for the sprint are dev-complete | JIRA sprint board — all stories in 'Done' |
| API documentation (OpenAPI spec) is published | Swagger UI accessible at /swagger-ui.html |
| Test environment is up and seed data is loaded | docker-compose ps — all services healthy |
| Test cases are reviewed and approved in JIRA/Xray | Xray test cycle — status = 'Ready' |

## 7.2  Exit Criteria (Release Approval)

| Criterion | Target | Measurement |
| --- | --- | --- |
| Test case execution rate | 100% | JIRA Xray execution report |
| Critical / High open defects | Zero | JIRA open issue filter |
| Regression suite pass rate | >= 95% | Allure report pass/fail ratio |
| Performance p95 latency | < 200 ms | k6 / JMeter HTML report |
| Automation coverage | >= 80% | Allure automation coverage panel |

# 8. Risk Register

| Risk ID | Risk Description | Probability | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R-01 | Payment gateway downtime in sandbox | Medium | High | Use WireMock stubs for unit tests; smoke test sandbox before each cycle |
| R-02 | Flaky UI tests due to async rendering | High | Medium | Explicit WebDriverWait; retry flaky tests up to 2× in CI |
| R-03 | Test data corruption between runs | Medium | High | DB reset script (seed-data.sql) executed before each suite run |
| R-04 | QA environment unavailability | Low | High | Docker Compose local stack; any team member can spin up in < 5 minutes |
| R-05 | Scope creep in late sprints | Medium | Medium | Strict change control; re-prioritise test suite with AI risk analysis |
| R-06 | DB performance bottleneck under load | Medium | High | Add indexes; connection pool tuning; Prometheus DB alert rules |

# 9. Effort Estimate & Timeline

| Phase / Activity | Duration | Effort (hrs) | Owner |
| --- | --- | --- | --- |
| Requirement Analysis | 3 days | 12 | QA Lead |
| Test Planning | 2 days | 8 | QA Lead |
| Test Case Design | 5 days | 20 | SDET |
| Test Environment Setup | 2 days | 10 | SDET + DevOps |
| Manual Test Execution | 5 days | 40 | QA Analyst |
| Automation Development | 7 days | 56 | SDET |
| Performance Testing | 3 days | 24 | SDET |
| Defect Management (ongoing) | — | 16 | QA Lead |
| CI/CD Integration | 2 days | 16 | SDET + DevOps |
| Test Closure | 2 days | 8 | QA Lead |
| Total | ~31 days | 210 | QA Team |

# 10. Approval

| Name | Role | Decision | Date |
| --- | --- | --- | --- |
| Adit Gupta | QA Lead | Approved | March 2025 |
| Dev Lead | Engineering | Approved | March 2025 |
| Product Mgr | Product | Approved | March 2025 |